## Guidance
FCDO Risk Register Template
Introduction This risk register template has been created to support: a) DG/directorate/post teams to document risk in advance of the rollout of digital tools. DGs, directors, HoMs should ensure that at a minimum risk escalations are documented, but can use the template to document a fuller set of risks they are overseeing if desired. b) Programme teams without access to digital risk tools through the Aid Management Platform (AMP). All programme teams with access to AMP should document risks there. Tab 1 is aligned to the AMP for consistency and to facilitate future transfer of data. Fields with grey column headings (as opposed to blue) are not replicated in AMP.
1 Risk Register Field Guidance The 'Number' field allows you to enter a unique identifier. The 'Risk Description' field should set out a clear and concise description covering the cause, the risk event which the cause triggers and the consequence of the risk event. The 'Risk Category' should identify the most appropriate risk category from the set of seven in FCDO's Risk Appetite Statement. The 'Proximity' field is the timeframe in which the risk might be expected to materialise. This is a best estimate. 'Gross Likelihood' and 'Gross Impact' are the initial risk assessments before any risk treatment has been carried out and together make a risk rating (Minor, Moderate, Major, Severe). We should consider impact on our delivery/performance and our reputation. 'Residual Likelihood' and 'Residual Impact' are our risk assessments after risk treatment and should be based on current progress in implementing mitigations, rather than future mitigations not yet implemented. 'Trend' indicates whether the risk is rising relative to last review. 'Risk Owner' is the individual who takes responsibility for treating the risk. This individual retains ownership for the life of the risk until formally changed on the register. The 'Mitigation Strategy' sets out how the risk is being treated. 'Comments' can be used to capture discussion points. 'Status' denotes whether a risk is active or closed. A closed risk is one that has materialised (become an issue), has gone away or has been successfully treated. 'Risk Appetite' should be taken from the Risk Appetite Worksheet for the appropriate category.
2 Risk Matrix This worksheet (numbered 2) shows the risk ratings designated by colour (Minor, Moderate, Major and Severe) as they are calculated in worksheet 1. This is not a live worksheet: it only shows risk examples but can be used to manually overlay risk entries from worksheet 1 for a more visual portfolio view. You might want to use this matrix only for the top risks.
3 Risk Appetite Risk appetite is the nature and extent of the risks that we are willing to take in order to achieve our objectives. For FCDO's Risk Appetite Statement, please click on the link in the adjoining cell. This sets out our organisational risk appetite and is not a ceiling for risk appetite set at directorate/post/programme levels. When setting the appetite in column B, do so for each risk category using a selection from the dropdown list. In column C, select which level of risk management the appetite applies to (DG/director/HoM/programme SRO). | Risk Appetite Statement
4 Workbook Management The formulae in this workbook are not protected in order to allow the addition of new rows into the risk register. To add new rows, copy a complete blank row and use the 'Insert Copied Cells' command. This will replicate the formulae. Source data for the formulae is included in a locked and hidden worksheet called 'Cell data Don't Change'

## 1 Risk Register
Risk Register: Add Name of DG/Directorate/Post/Programme
Number | Risk Description (cause, event, consequence) | Risk Category | Proximity | Gross Likelihood | Gross Impact | Gross Risk Rating (autofills) | Mitigation Strategy (including timescales) | Residual Likelihood | Residual Impact | Residual Risk Rating (autofills) | Trend | Risk Owner | Progress in Implementing Mitigation Strategy | Last Updated (DD/MM/YY) | Status | Risk Appetite | Within Appetite? | Escalated To You By? (Name of Risk Owner) | Escalated To You For? Information or Support | Date Escalated To You (DD/MM/YY) | Escalated Onwards To? (Name of Senior Manager/Board) | Escalation Onwards For: Information or Support | Date Escalated Onwards (DD/MM/YY) | Date Removed
|  |  |  | Likely | Insignificant | Minor |  |  |  | #N/A
[6 empty] | #N/A |  |  |  | #N/A
[6 empty] | #N/A |  |  |  | #N/A
[6 empty] | #N/A |  |  |  | #N/A
[6 empty] | #N/A |  |  |  | #N/A
[6 empty] | #N/A |  |  |  | #N/A
[6 empty] | #N/A |  |  |  | #N/A
[6 empty] | #N/A |  |  |  | #N/A
[6 empty] | #N/A |  |  |  | #N/A
Note on A3: Add a unique identifier.
Note on B3: Set out a clear and concise description covering the cause, the risk event which the cause triggers and the consequence of the risk event.
Note on C3: Choose the best fit from one of the 7 drop-down options using the category definitions in the FCDO Risk Appetite Statement.
Note on D3: Proximity is the timeframe in which the risk might be expected to materialise. This is a best estimate - select the most appropriate option.
Note on E3: Likelihood of the risk before risk treatment - select the most appropriate option.
Note on F3: Impact of the risk on delivery/reputation before risk treatment - see risk matrix in guidance and select the most appropriate option.
Note on G3: This is a combination of likelihood and impact - autocompletes.
Note on H3: Set out how the risk is to be treated. Define a set of actions which you can update in the Progress column.
Note on I3: Likelihood of the risk after risk treatment - select the most appropriate option.
Note on J3: Impact of the risk on delivery/reputation after risk treatment - select the most appropriate option.
Note on K3: This is a combination of likelihood and impact - autocompletes
Note on L3: Change in risk relative to last review - stable, rising, falling.
Note on M3: Add the name of the individual who takes responsibility for treating the risk.
Note on N3: Set out the progress achieved since the last review in implementing the mitigation strategy in column H, including dates.
Note on O3: Last updated means when changes are made. A risk which is reviewed but not changed does not need an update. All risk details are assumed to be current.
Note on P3: Select 'open' or 'closed'. A closed risk may be one which has been successfully treated ; where the risk has disappeared; or where the risk has materialised into an issue. Closed risks may stay on the register to provide an audit trail but can be filtered from the normal view.
Note on Q3: Select the approriate option for the risk category, consistent with the 'Risk Appetite' worksheet
Note on R3: Does the Residual Risk Rating (column K) exceed the 'Risk Appetite' (column Q)?
Note on S3: If the risk has been escalated to you (because it is above appetite, or requires further support) please enter the name of the Risk Owner who escalated it to you.
Note on T3: Indicate if the risk was escalated for information or support.
Note on U3: Enter the date on which the risk was escalated to you.
Note on V3: If the risk has been escalated to you (because it is above appetite, or requires further support) please enter the name of the senior manager/Board you are escalating to.
Note on W3: Indicate if you are escalating the risk for information or support.
Note on X3: Add the date on which the risk was escalated onwards.
Note on Y3: Add the date on which the risk entry no longer requires attention (information or support) on this register. The risk will most like remain on its original register and is not the same as closing the risk.

## 2 Risk Matrix
Risk Matrix
(Note that this is not an automated matrix)
Likelihood | Almost Certain | Minor | Moderate | Major | Severe
Highly Likely
Risk Reference:
| Likely | [5 empty] | Risk category X | 1 | Risk 1
[8 empty] | 2 | Risk 2
[8 empty] | 3 | Risk 3
[8 empty] | 4 | Risk 4
| Possible | [6 empty] | 5 | Risk 5
[7 empty] | Risk category X | 6 | Risk 6
[8 empty] | 7 | Risk 7
[8 empty] | 8 | Risk 8
| Unlikely | [6 empty] | 9 | Risk 9
[8 empty] | 10 | Risk 10
|  | Insignificant | Minor | Moderate | Major | Severe
Impact
7.
5.
2.
3.
4.
1.
6.
→
→
→
→
→
→

## 3 Risk Appetite
Risk Appetite
Set your appetite appropriately for your business area/programme, drawing on the FCDO Risk Appetite Statement. See link below.
Risk Appetite Statement
Risk Category | Appetite | Set By (Name/Title - SRO/HoM/Director/DG) | Date Set (DD/MM/YY) | Updated Appetite | Change Date (DD/MM/YY)
Strategy and Context
Policy and Programme Delivery
Public Service Delivery and Operations
People
Safeguarding
Financial and Fiduciary
Reputational
Note on B5: Select the appropriate option
Note on C5: Add name and title (SRO, HoM, Director or DG) of the individual taking accountability for the risk appetite. The title denotes the business unit level at which the appetite is set
Note on E5: Select the appropriate option

## Cell data Dont Change! (hidden)
Impact | Likelihood | Appetite |  | Proximity | Escalation Decision | Escalation Level
Insignificant | Unlikely | Minimal | Minor | 0-3months | Not accepted – content with director oversight | Project or Programme
Minor | Possible | Cautious | Moderate | 3-6months | Accepted for additional DG oversight | Mission or Department
Moderate | Likely | Receptive | Major | 6-12months | Accepted for additional DG oversight and support | Directorate
Major | Highly Likely | Eager | Severe | >12 months |  | Directorate General
Severe | Almost Certain
Escalation Type
For Information
For Support
Yes | No
Minor | Moderate | Major
Trend
→ | ↑ | ↓ | New
PRR Strategic Risk Report References
Almost CertainInsignificant | Minor | 1 Strategy and context - HMG coherence
LikelyInsignificant | Minor | 2 Strategy and context- Strategic competition
PossibleInsignificant | Minor | 3 Strategy and context - Conflict and security
UnlikelyInsignificant | Minor | 4 Strategy and context - Allies and partners
UnlikelyMinor | Minor | 5 Strategy and context - Global economy
PossibleMinor | Minor | 6 Policy and programme delivery - UK/EU future relationship negotiations
LikelyMinor | Minor | 7 Policy and programme delivery - COVID-19 international response
Almost CertainMinor | Moderate | 8 Policy and programme delivery - Supply chains
UnlikelyModerate | Minor | 9 Policy and programme delivery -Climate and environment
PossibleModerate | Moderate | 10 Policy and programme delivery - Humanitarian response
LikelyModerate | Moderate | 11 People - Workforce
Almost CertainMajor | Severe | 12 People - Change management
UnlikelyMajor | Moderate | 13 People - Duty of care
Highly Likelyinsignificant | Minor | 14 Public service delivery and operations - Crisis and consular
Highly LikelyMinor | Moderate | 15 Public service delivery and operations - Estate and security
Highly LikelyModerate | Major | 16 Public service delivery and operations - Data and cyber-security
Highly LikelyMajor | Severe | 17 Financial and fiduciary - Public spending commitments
Highly LikelySevere | Severe | 18 Financial and fiduciary - Fraud and aid diversion
PossibleMajor | Major | 19 Safeguarding - Sexual exploitation, abuse and harassment
LikelyMajor | Major | 20 Reputational - Reputation
Almost CertainMajor | Severe
Almost CertainModerate | Major
UnlikelySevere | Major
PossibleSevere | Severe
LikelySevere | Severe
Almost CertainSevere | Severe
Reputational
Financial and Fiduciary
Safeguarding
People
Public Service Delivery and Operations
Policy and Programme Delivery
Strategy and Context